## Sheet1
|  |  |  | Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7 |  | Day 8 |  | Day 9 |  | Day 10 |  | Day 11 |  | Day 12 |  | Day 13 |  | Day 14 |  | Day 15 |  | Day 16 |  | Day 17 |  | Day 18 |  | Day 19 |  | Day 20 |  | Day 21
|  |  |  | 2011-03-23 |  | 2011-03-24 |  | 2011-03-25 |  | 2011-03-26 |  | 2011-03-27 |  | 2011-03-28 |  | 2011-03-29 |  | 2011-03-30 |  | 2011-03-31 |  | 2011-04-01 |  | 2011-04-02 |  | 2011-04-03 |  | 2011-04-04 |  | 2011-04-05 |  | 2011-04-06 |  | 2011-04-07 |  | 2011-04-08 |  | 2011-04-09 |  | 2011-04-10 |  | 2011-04-11 |  | 2011-04-12
Item | Hours | Owner | Status | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Worked | Remaining | Hours Worked | Hours Left
Finalize basic graphical style for the site | 10 | jmataya | Unassigned | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10
Synchronize login | 6 | jmataya | Unassigned | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6
Ammend the database with profile information | 1 |  | Unassigned | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1
Customize forum display properties | 10 |  | Unassigned | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10
Create the profiile page | 10 |  | Unassigned | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template Item | 0 |  | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Day 2 = [Day 1]+1
Day 3 = [Day 2]+1
Day 4 = [Day 3]+1
Day 5 = [Day 4]+1
Day 6 = [Day 5]+1
Day 7 = [Day 6]+1
Day 8 = [Day 7]+1
Day 9 = [Day 8]+1
Day 10 = [Day 9]+1
Day 11 = [Day 10]+1
Day 12 = [Day 11]+1
Day 13 = [Day 12]+1
Day 14 = [Day 13]+1
Day 15 = [Day 14]+1
Day 16 = [Day 15]+1
Day 17 = [Day 16]+1
Day 18 = [Day 17]+1
Day 19 = [Day 18]+1
Day 20 = [Day 19]+1
Day 21 = [Day 20]+1

## Preferences
Start Date | 2011-03-23 | Unassigned
In Progress
Completed